## EVENT Risk Register Template
EVENT RISK ASSESSMENT FOR SMALL TO MEDIUM This Risk Assessment forms part of the Event Management Plan Please refer to the Event Risk Assessment Guide when completing this document. The Guide can be found here Note: This template is not limited to the information contained and not all sections will be applicable to each event. It is expected the Event Organisers customise the Event Risk Assessment to ensure it reflects the hazards, risks, and controls specific to their event.
| Event Name: | [6 empty] | Event Location:
| Event Date: | [6 empty] | Expected Attendance:
| Event Times: | [6 empty] | Date Risk Register Completed:
| STEP 1 |  |  | STEP 2 |  |  |  | STEP 3 | STEP 4 |  |  |  | STEP 5 | STEP 6
| Identified Risk What can go wrong? How can it go wrong? |  | Does this risk apply to your event? Choose Yes or No from drop down box | Risk Assessment (risk level BEFORE your controls are in place) Choose rating from drop down box |  |  |  | Control (delete or add to this example list) | RESIDUAL RISK ASSESSMENT (risk level AFTER your risk controls are in place) |  |  |  | Responsibility (Person/s responsible for managing control) | Control Implemented (Choose Yes or No from drop down box)
|  |  |  | Severity | Likelihood | Risk Level | Risk Score |  | Severity | Likelihood | Risk Level | Risk Score
WEATHER | Rain | • Water on road, event grounds and paths causing slips and falls | [5 empty] | • Event Staff identify wet and boggy locations causing hazard • Hazards sectioned off with traffic cones, bollards or hazard tape • Weather is monitored closely before and during the event
|  | • Heavy prolonged rain caused postponement or cancellation of event | No |  |  |  |  | • Postponement and cancellation policy in place • Stop event/restart procedure in place • Alternative locations booked • Vendors notified • Weather is monitored closely before and during the event
|  | • Insufficient undercover protection for event patrons | [5 empty] | • Attendees can seek temporary shelter in marquees or at nearby premises
| Lightning and Storms | • Attendee, Vendor, Contractor or Event staff struck by lightning. | [5 empty] | • Adverse weather procedure in place • Medical response plan in place • Contractors, vendors, staff, volunteers are directed to stop work and take cover • Weather is monitored closely before and during event • Stop Event/restart procedure in place • Direct attendees to take cover
| High Winds | • Very high winds bring down tree/ branches onto surrounding roads. | [5 empty] | • Check the area in week prior to the event for any potential loose branches or debris and report to local council seeking removal. • If tree falls on road report to 000. Ensure First Aid is in place at event site. • Incident reporting procedure in place. • Alert Traffic supervisor to allow emergency vehicle access if required. • Weather is monitored closely before and during event
|  | • Very high winds collapse marquees, signage, and fencing or bring down tree/branches on event site. | [5 empty] | • Postponement and cancellation policy in place. • Event stop/restart procedure in place. • Contractors, vendors, staff, volunteers are directed to stop work and take shelter. • Infrastructure dismantled if safe to do so. • Marquees installed as per manufacturer’s instructions. • Engineer Certification received for large infrastructure 20sqm and over. • Stop/restart procedure in place. • Direct patrons to undercover locations. • Follow evacuation procedure. • Notify traffic controller of approaching emergency vehicles.
| Extreme Heat | • Extreme heat causing heat exhaustion. | [5 empty] | • Monitor weather before and during event • Ensure adequate drinking water is available at the site – free or for sale. • Increase seating in shaded areas. • Brief Staff, volunteers and stallholders and suppliers about keeping hydrated, bringing sunscreen and hats.
| Bushfire | • Major bush fire emergency affects event site. | [5 empty] | • Consultation with RFS during event planning. • Emergency Management Plan in place, all stakeholders understand their role including media liaison. • Brief volunteers on emergency plan • Medical Plan in place.
COMMS | Communication Failure | • Communications failure. • General public unaware of event. | [5 empty] | • Marketing/advertising plan in place in lead up to event • Website kept up to date • Organisers to undertake letterbox drops to local businesses and residents impacted by road closures, parking or event generally. • Notification placed local paper prior to event with road closure times.
|  | Communication equipment failure. | [5 empty] | • Multiple communication options will be used. Mobile phones (charged prior to event) • Two-way radios (if in use will be tested prior to event and volunteers instructed in use) • Face to face meetings.
|  | • Mobile phone reception not available at all times to event team. | [5 empty] | • Multiple communication options will be used. • A two-way radio system will be utilised. • Face to face meetings.
|  | • Emergency evacuation protocol announcements not communicated correctly to patrons. | [5 empty] | • All staff and persons with roles in the Emergency Plan to be trained to understand their role during an emergency and how information is communicated. • Have a pre- prepared generic statement that can be adapted for the situation to address attendees and stall holders. • Have a pre-prepared generic media statement that can be adapted to the situation. • Assign one person to be the spokesperson for the media to provide clear, concise and timely information to the patrons (NB: including social and local media). • Committee to consider under what circumstances it would activate the Emergency Management Plan.
ON SITE ISSUES AND HAZARDS | Fall from Heights | • Fall from stage or structure causing impact injury. | [5 empty] | • Ensure all staff, volunteers, contractors are aware of the site-specific risks and site rules. • Security and crowd barriers to prevent access to temporary stage. • Rear of stage clearly identified to prevent falls. • Access to stage will be via stairs (must include a handrail and comply with AS1657)
|  | • Fall from height during bump-in/bump-out. | [5 empty] | • Ensure all staff, volunteers, contractors are aware of the site-specific risks and site rules. • Use of correct working at heights plant e.g. scaffold and fall arrest equipment where required. • Correct use of a ladders.
| Falling Objects | • Objects falling from height in work zones. | [5 empty] | • Ensure all staff, volunteers, contractors are iaware of the site-specific risks and site rules. • All work zones with overhead works to be identified with barricades to ensure all persons in the area are aware. • Use of correct PPE for high risk works including Hard Hats. • Appoint Site Manager to monitor event site during event to identify any overhead hazards that have developed as event has progressed.
| Manual Handling | • Manual handling injury sustained by workers lifting/using inappropriate manual handling techniques. | [5 empty] | • Ensure all staff, volunteers, contractors are aware of the site-specific risks and site rules in regard to correct lifting procedures. • Use of trolleys and lifting equipment as a preference
| Electrical Hazard | • Malfunction of electrical equipment. | [5 empty] | • All equipment to be tested and tagged in accordance with AS3000-2007. • Residual Current Devices (RCDs) to be used onsite. • All stallholders and suppliers advised in information kits of event site minimum electrical requirements. • Event Marshall to complete check of tags on all electrical equipment to ensure testing is current. • All electrical cords to either be placed above head height between power source and equipment OR inside cable trays. • Wherever possible cords to be kept away from public thoroughfares to avoid trip hazards and ensure safety. • Avoid joining power cords with adaptors. • In wet weather ensure protection of leads and power points. • Prior to event request power activation by Council and test on day before event.
| Infrastructure Failure | • Generators onsite fail | [5 empty] | • Source generator units from reputable supplier. • Complete pre-start checks and fuel levels prior to event. • Back-up generator on standby. • Stallholders and amusement device operators advised to check generators before coming on site. • Stallholders and amusement device operators advised that generators should be sseparated from public access e.g. located back of house or barrier/fencing installed to prevent public access
|  | • Unprotected electrical wires or cables cause pedestrian hazard. | [5 empty] | • Site layout to be designed to minimise electrical cable runs over high traffic locations. • Cable trays and covers to be used as alternative.
| Movement of Plant, Equipment and Vehicles Onsite | • Collision with other vehicles or people onsite. | [5 empty] | • All staff and contractors briefed on site rules. • Vehicles to move through event precinct at walking pace with escort and hazard lights on. • Contractors to follow instructions of traffic controllers or Site Managers for access to site . • Organiser will istallholder’ on site rule and reinforce on entry. • All vehicles to unload as quickly as possible and exit site. • All unattended vehicles to have ignition keys removed to avoid unauthorised or unlicensed drivers gaining access (including forklifts)
|  | • External emergency adjacent or near event. | [5 empty] | • Any changes to road closures or redirection of traffic, event organisers are to follow Police instructions. • NSW Police manage off site incidents
|  | • Event site bump-in and establishment delayed. | [5 empty] | • Ample bump-in schedule to be developed. • Event Marshall and volunteer tasks allocated prior to event to ensure smooth bump in.
|  | • Event site not available due to inclement weather. | [5 empty] | • Check with Council if site still open. Alternative venues arranged. • Weather monitored. • Weather “Stop Event” protocol activated
|  | • Event site ground surface not in suitable condition for infrastructure | [5 empty] | • Pre-event inspection of site to identify alternative location or design. • Monitor weather and forecasts.
|  | • Area upgrade or maintenance not completed in time for event bump-in. | [5 empty] | • Event application submitted to council in required timeframe to allow for any planned works and mowing schedules. • Pre-event inspection of site to identify alternative location or design.
|  | • Lighting insufficient during event or overnight for security purposes. | [5 empty] | • Pre-event inspection of site to identify areas that require additional lighting. • Arrange temporary or portable lighting. • Ensure security guards vehicles are well equipped with flood lights and spotlights.
| Event Catering | • Incorrect food handling and storage processes. | [5 empty] | • Food vendor food handling documentation checked prior to event commencement. • Food stalls provided with Council’s food stall information
|  | • Inadequate storage of cooking utensils including knives. | [5 empty] | • Ensure food vendors have cooking utensils secured safely. • Stall Holders pre-event informationinclude advice that it is Stall Holder’s responsibility to ensure cooking utensils secured safely from public access, especially knives.
|  | • Inadequate separation of cooking processes and equipment; BBQ utensils including BBQ smokers and rotisseries. | [5 empty] | • Pre-event information kit to include advice on separation of cooking areas from public and to refer to NSW Food Authority Guidelines. • Conduct a pre-event inspection. • Ensure vendor stalls are designed to protect patrons from hot surfaces. • Cooking equipment not to be left unattended
|  | • Spillage from cooking equipment. | [5 empty] | • Pre-event information kit to include advice that all cooking oils and water to be removed from site. • Conduct a pre- event inspection. • Ensure waste oil disposal processes are compliant (not disposed in onsite garbage bins, toilets or drains). • Ensure spill kits are available. • Ensure waste oil containers are stored on oil resistant base e.g., not directly on grass or ground.
| Waste Management | • Rubbish is left onsite from day visitors prior to bump-in. | [5 empty] | • Event site to be cleaned with existing garbage bins emptied prior to event commencement. • Waste Management Plan in place. • Waste Management Provider engaged
|  | • Excessive rubbish is left after the event | [5 empty] | • Waste Management Plan in place. • General clean-up of site and relocate bins to pick up point.
| Amusement Rides | • Accident/Incident involving Amusement Rides | [5 empty] | • Obtain and comply with necessary permits, approvals and licenses, legislation, standards and guidelines issued by Council and other government agencies • Amusement structure meets Australian Standard • Inflatables not in during periods of strong wind/heavy rain • inflatables have back up power source • First aid officer on site • Safety fencing//barriers • Operator holds current competency to operate equipment and is instructed on Safe Operating and Emergency Procedures • Use only professional and reputable amusement ride operators • Emergency Management Plan
| Animal Handling/Display | • Accident/Incident involving Animal Display | [5 empty] | • Hand washing available or hand sanitation dispenser • Reputable provider with animals in good health • Signage stating requirements for children must be accompanied by parent or guardian • Roped / Barricaded / Fenced designated showing areas • Signage advising patrons not to enter show / parade area • Competent and experienced animal handlers only • First aid officer onsite
| Pyrotechnics/Fireworks | • Accident/Incident involving Fireworks | [5 empty] | • Obtain and comply with necessary permits, approvals and licenses, legislation, standards and guidelines issued by Council and other government agencies • Insurance obtained as per CoS Public Events Planning Guide • Site Plan includes location fire extinguisher and fire hose reels • Use of competent, qualified and licenced fireworks contractor • Letter drop to nearby residents • No fireworks used during Total Fire Ban • Department Fire and Emergency Services notified of display and on call to respond to any fire situations • Wind monitored on the day so that site can be adjusted to compensate
| Production and Delivery Schedule | • Unscheduled or late arrival of equipment. | [5 empty] | • Production schedule circulated to all contractors prior to event. • Site Manager will be onsite to manage the contractors in event of a later delivery.
PEOPLE AND STAFFING | Medical Issues | • First Aid treatment - suspected heart attack, asthma attack or medical emergency | [5 empty] | • Qualified First Aid on site. • First Aid station well signposted. • All volunteers, stall holders, suppliers, aware of first aid location. • Emergency vehicle access will be maintained at all times. • If 000 called, Traffic Controller to be advised to manage site access.
|  | • Offsite emergency where a person is required to leave quickly e.g., access parking, manoeuvre through crowded areas. | [5 empty] | • Display vehicles will be advised in pre-event information pack, and on arrival, of scheduled exit time. • Traffic Controller to supervise exit of any vehicle that needs to leave event space before scheduled exit time.
| Crowd Management | • Unprecedented crowd numbers causing event. site to fill beyond capacity creating crush in public place. | [5 empty] | • Site layout designed to avoid bottlenecks. • Event Manager and Sit Manager to monitor crowd flow and redirect crowds if required. • Volunteers to be briefed prior to event on their role in assisting with crowd flow. • Crowd Management Plan in place. • If crowds becoming unmanageable request assistance from Police.
|  | • Emergency services unable to reach emergency due to overcrowding. | [5 empty] | • 4m wide emergency vehicle access to be maintained on any closed road. • Emergency vehicle access to be maintained into site. • Emergency vehicle to enter under flashing lights and siren if necessary. • Traffic Controller advised to assist emergency vehicle to access site. • NSW Police asked to assist if required.
|  | • Crowd causing egress obstruction in the event of an emergency. | [5 empty] | • Crowd Management Plan in place. • Event Marshals and volunteers briefed on their role in dispersing crowds obstructing egress. • Event organisers to have preprepared message for use on PA equipment to assist in crowd movement. • NSW Police asked to assist if required.
| Contractors | • Unauthorised people onsite creating security and safety risk. | [5 empty] | • A list of authorised contractors at point of entry for cross checking. • Issue entry passes issued to authorised contractors and suppliers as part of pre-event planning. • Unauthorised people asked to leave by security and event manager. • Call Police for assistance if refuse to leave.
| Vendors and Stallholders | • Unauthorised vendors and suppliers onsite creating security and safety risk. | [5 empty] | • A list of authorised stallholders at point of entry for cross checking. • Entry passes issued to authorised stall holders or vendors as part of pre-event lanning • Only authorised stalls/vendors allowed to set up. • Ccalmly ask unauthorised people to leave. Event organiser will call Police for assistance if unauthorised operators refuse to leave.
| Event Staff/Volunteers | • Event Staff and volunteers not understanding site rules and not leading by example creating security and safety risk | [5 empty] | • Event Staff and volunteers briefed prior to event on site rules.
|  | • Volunteers fail to arrive or volunteers numbers inadequate to support the event. | [5 empty] | • Ensure volunteer numbers are confirmed prior to event. • Have a list of back-up volunteers in case of sickness. • A list of assigned duties distributed prior to event.
| Working with Children | • Event Staff/ volunteers required to have a current Working with Children Check | [5 empty] | • Prior to event all EventStaff/volunteers to provide evidence of their current Working with Children check. • Details on how to apply for a Working with Children check provided to staff and volunteers
SECURITY | Protests Protest related to event. | • Vandalism to event site or surrounding area overnight. | [5 empty] | • Security patrol scheduled. • Report offensive graffiti to Council’s or attempt to cover up until removed. • Do a routine check of the event site prior to set up and arrival of stall holders/amusements and for a clean up. • Report vandalism to Police and Council.
|  | • Patrons and event representatives are blocked from accessing the event site. | [5 empty] | • Notify and work with Police. • Assess and work with traffic controller or Site Managerto find an alternate entry point. • If required direct patrons to new entry point away from protesters. • Monitor situation and return access to normal location when appropriate. • Complete an Incident Report for Police and Council
|  | • Physical conflict between event representatives and protestors. | [5 empty] | • Avoid direct engagement with protesters. • Notify Police providing details on protest theme, numbers, mood of protesters and request assistance. • Move events team/volunteers away to a safe location to avoid protesters. • Liaise with Police on whether or not to ‘Stop Event’. • Complete an Incident Report for Police and Council.
| Bomb Threat | • Call received but not enough information captured | [5 empty] | • Provide a checklist to Event Staff of details to collect if threat is verbal. • Event organiser Ensure all Event Staff are fully briefed on information required. • Emergency Planl process to be followed.
| Child Safety | • Suspicious person loitering near public amenities or children’s play area. | [5 empty] | • Identify potential risk sites. • Brief Event Staff to monitor these sites. • Report any suspicious behaviour or loitering for long periods of time to Security for assessment. • Report to Police if required.
| Armed Active Threat Suspicious Behaviour (this can be mentally unstable, drug affected, or terrorism related). | • Armed active threat/ suspicious behaviour. | [5 empty] | • Brief staff to be vigilant for any unusual agitated or erratic behaviour or anyone acting suspiciously, • Report the behaviour to the Security for assessment. • If concerned tl call Police immediately and isolate the area around any package left on site. • Do not approach the person, keep a safe distance and monitor their movements so can inform Police on arrival.
| Hostile Vehicle | • Hostile Vehicle Mitigation in place
ENVIRONMENT | Property | • Event area lawns and trees damaged by equipment. | [5 empty] | • All suppliers, delivery drivers and vendors must follow site rules and event staff instructions. • All vehicle movements must be escorted with walking spotter in front. • All vehicles (particularly with high loads) must abide with speed limit to minimise damage to trees and grass. • Track matting must be installed for vehicle movements where applicable to protect lawn surface from heavy vehicle damage. • All damage to trees or grass must be reported to event organisers. • Check with Council for any restricted area for vehicles. • Monitor weather conditions and avoid areas that may be impacted by excessive rain.
|  | • Sufficient bins ordered to manage litter. | [5 empty] | • Evaluate existing bins tand order extras from Council to reduce overflow of rubbish. • Engage a Wate Management Provider • Waste Management Strategy in place
| Accessible (Disability) Access | • Failure to provide appropriate facilities for people with disabilities creating legal issues for event organiser. | [5 empty] | • Comply with regulations for people with a disability. Pre-event site inspection to include review of access. • Arrange for temporary accessible (disabled) parking to replace any displaced accessible (disabled) parking due to road closures (include in traffic plan). • Ensure that temporary accessible (disabled) parking is well signposted, and locations advised on website and on any event brochures. • Ensure traffic controllers are aware of locations for accessible (disabled) parking. • Ensure that stall/amusements layout does not block access to any kerb ramp from footpath to road.
| Event is Located Near Water | • Proximity to Beach, Lake or Creek poses a drowning hazard to attendees | [5 empty] | • Warning signs • supervisors, life guards, police boat, seurity guards, stage announcements • Installation of approved barrier that complies to Australian Standards, ambulance on standby • Signage installed and lifesaving devices available • Event program supervisors qualified for water activities with knowledge of site and possible hazards • Supervised water activities will be conducted in appropriate and safe areas • Safety officer and first aid officer onsite through event
| Damage to underground utilities and servicesoise | • Underground utilities damaged during bump-in | [5 empty] | Comple a Dial Before you Dig survey • Site plan includes location of underground utilities including water, electricity and telecommunications •Qualified and licenced plumber and electrician on site or on call during event • Regular site inspections to identify and report site issues
| Excessive Noise | • Noise from event results in complaints from residents | [5 empty] | • Obtain and comply with necessary permits, approvals and licenses issued by Council and other government agencies • Noise Management Plan • Use of sound barriers and other noise controls including site layout and event timings/duration • Communication with residents e.g. letter drop
| Inadequate Toilet Facilities | • Toilets overflowing due to overuse | No |  |  |  |  | Adequate number of toilets provided and maintained • Engagement of reputable and professional provider • Ensure disabled toilets available and accessible • Maintenance staff available during event to ensure toilets kept operational and in a clean state • Any toilet issues must be immediately relayed to cleaners on site and site manager • Toilet hook up conducted by qualified plumber
TRAFFIC MANAGEMENT | Implementation and management of Road Closures | • Injury to event staff during set up and dismantling of traffic management due to poor visibility. | [5 empty] | • Shadow vehicles with flashing lights used to protect personnel; • Aall personnel to wear high visibility vests with retro reflective strips • Engage Traffic Management Company to implement Road Closures • Traffic Management Plan in place
|  | • Road users misreading the traffic management arrangements, crashing into the signs and devices and causing injury | [5 empty] | • Traffic management to be set up in accordance with the Traffic Management Plan and the Traffic Guideance Scheme • Engage Traffic Management company to implement Road Closures • Ensure Road Closures are in place and working effectively before commencing event
|  | • The increase in traffic volumes around the venue caused by the event may cause congestion and delays. | [5 empty] | • Ample signage advising Event Ahead to be displayed; • Nearby residents and businesses notified of event and impacts • Event Road Closures and parking arrangements advertised
|  | • Signage being vandalised or removed by members of the public causing confusion and vehicles entering event and pedestrian areas | [5 empty] | • Engage Traffic Management Company to implement and Manage Road Closures • Road Closures implemented in accordance with Traffic Management Plan and Traffic Guidance Scheme • Ensure enough Traffic Marshals are in place • Regularly monitor traffic arrangements. monitoring of signage and devices by traffic management personnel;
Add New
Add New
Add New
Add New
Add New
Add New
Add New
Add New
Add New
Add New
Add New
Add New
Add New
Add New
Add New
Add New
Add New
Add New
Add New
Add New
Add New
Add New
Add New
Add New
Add New
Add New

## Sheet1 (hidden)
Does This risk apply to your event
Yes
No

## City of Swan Risk Tables (hidden)
| RISK ASSESSMENT MATRIX | [5 empty] | LIKELIHOOD TABLE: LIKELIHOOD OF IMPACT
Consequence
|  | Insignificant | Minor | Moderate | Significant | Severe | Descriptor | Description of Likelihood
Likelihood | Almost Certain | Medium (5) | High (10) | High (15) | Very High (20) | Very High (25) | Almost Certain | The event is expected to occur, more than once a year
| Likely | Low (4) | Medium (8) | High (12) | High (16) | Very High (20) | Likely | The event will probably occur, once a year event
| Possible | Low (3) | Medium (6) | Medium (9) | High (12) | High (15) | Possible | The event should occur, once in 5 year event
| Unlikely | Low (2) | Low (4) | Medium (6) | Medium (8) | High (10) | Unlikely | The event could occur but probably won’t, once in 10 year event
| Rare | Low (1) | Low (2) | Low (3) | Low (4) | Medium (5) | Rare | The event is not expected to occur, once in 20 year event
CONSEQUENCE OF TABLE:SEVERITY OF IMPACT
[7 empty] | Descriptor | Description of Consequence
[7 empty] | Insignificant | No injuries, low financial loss, low reputational damage, insignificant environmental impact
[7 empty] | Minor | First Aid required, medium financial lose, minor impact on event, low profile media attention, minor environmental impact
[7 empty] | Moderate | Medical treatment required, high financial lose, external assistance required, public complaint, moderate environmental impact
[7 empty] | Significant | Extensive injury, major halt to event, major financial loss, emergency services required, high media attention, damage to reputation, significant environmental impact
[7 empty] | Severe | Death, potential prosecution, catastrophic financial loss, irreversible reputational damage, severe environmental impact

## Lists (hidden)
Likelihood |  |  |  |  | Yes | Yes
A | A-Almost Certain |  |  |  | No | No
B | B-Likely |  |  |  |  | ALARP
C | C-Possible
D | D-Unlikely
E | E-Rare
N/A | N/A
Consequences
5 | 5-Severe
4 | 4-Significant
3 | 3-Moderate
2 | 2-Minor
1 | 1-Insignificant
N/A | N/A
Concatenate | Consequences | Likelihood | Risk Level | Risk Rank
5-SevereA-Almost Certain | 5-Severe | A-Almost Certain | Very High | 25
5-SevereB-Likely | 5-Severe | B-Likely | Very High | 20
4-SignificantA-Almost Certain | 4-Significant | A-Almost Certain | Very High | 20
5-SevereC-Possible | 5-Severe | C-Possible | High | 15
4-SignificantB-Likely | 4-Significant | B-Likely | High | 16
3-ModerateA-Almost Certain | 3-Moderate | A-Almost Certain | High | 15
5-SevereD-Unlikely | 5-Severe | D-Unlikely | High | 10
4-SignificantC-Possible | 4-Significant | C-Possible | High | 12
3-ModerateB-Likely | 3-Moderate | B-Likely | High | 12
2-MinorA-Almost Certain | 2-Minor | A-Almost Certain | High | 10
5-SevereE-Rare | 5-Severe | E-Rare | Medium | 5
4-SignificantD-Unlikely | 4-Significant | D-Unlikely | Medium | 8
3-ModerateC-Possible | 3-Moderate | C-Possible | Medium | 9
2-MinorB-Likely | 2-Minor | B-Likely | Medium | 8
1-InsignificantA-Almost Certain | 1-Insignificant | A-Almost Certain | Medium | 5
4-SignificantE-Rare | 4-Significant | E-Rare | Low | 4
3-ModerateD-Unlikely | 3-Moderate | D-Unlikely | Medium | 6
2-MinorC-Possible | 2-Minor | C-Possible | Medium | 6
1-InsignificantB-Likely | 1-Insignificant | B-Likely | Low | 4
3-ModerateE-Rare | 3-Moderate | E-Rare | Low | 3
2-MinorD-Unlikely | 2-Minor | D-Unlikely | Low | 4
1-InsignificantC-Possible | 1-Insignificant | C-Possible | Low | 3
2-MinorE-Rare | 2-Minor | E-Rare | Low | 2
1-InsignificantD-Unlikely | 1-Insignificant | D-Unlikely | Low | 2
1-InsignificantE-Rare | 1-Insignificant | E-Rare | Low | 1
N/A | N/A | N/A | N/A | N/A
CONTROLS RANKING |  |  |  | Control Rank
PPE | Low |  |  | 1
PPE | Medium |  |  | 2
PPE | High |  |  | 3
Procedures | Low |  |  | 4
Procedures | Medium |  |  | 5
Procedures | High |  |  | 6
Engineering | Low |  |  | 7
Engineering | Medium |  |  | 8
Engineering | High |  |  | 9
Percentage Complete
0%
10%
20%
30%
40%
50%
60%
70%
80%
90%
100%